## Issues
Sr.No. | Issues Raised | Issue Raised On | Task Delivered | Status | Priority | Rank | Resource | Next line of Action | Remarks
1 | Move Save button to right top of the Form. | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
2 | To check with the Screen Resolution | 2022-03-08 |  | Pending | High | 7 | Amandeep | To connect with client for session and check the Resolution setup
3 | Proper Alignment of the form -Left align all the header fields. -Equal spacing/margin between the fields. -Left align Upload attachment/attachment fields. | 2022-03-08 |  | In progress | Low |  | Amjad | To be resolved
4 | Make the font size same for the whole form | 2022-03-08 |  | In progress | Low |  | Amjad | To be resolved
5 | Option to enter date manually | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
6 | Currently on Account Selection, System select the first record by default. This should not happen. | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
7 | Show whole Item Type on screen currently it is partially visible. | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
8 | On item Name field, currently Group code and name both are appearing. Show only Item name. | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
9 | Make all the price values having 2 decimal places. Example if entered 35.45 then it will be as it is and if entered 35 it should be 35.00 | 2022-03-08 | 2022-03-25 | Done | Medium | 5 | Amandeep | Delivered on UAT
10 | Make the Item line editable before submitting the form by user. | 2022-03-08 | 2022-03-25 | Done | Medium | 1 | Amandeep | Need to discuss as this will be a big change. | Make update button enabled only if user makes any changes in the line
11 | Where ever the user code is appearing for submitted by/Approved by/Released by- change it to name instead of code. -On Home Screen(Done) -Forms in Queue(Done) -Price Variance History(Done) | 2022-03-08 |  | Done |  |  |  | Delivered on UAT | #NAME?
12 | On Home screen of each form, left align the content of table and center align the table. | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
13 | Remove Manage Hierarchy and Manage Notification from Menu | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
14 | On Forms in Queue - Set Status - Awaiting Approval by default on screen. | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
15 | Correct the "Volume" spelling on all the forms. | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
16 | When user uploads customer with duplicate record, system throws an long error. Check that error and change the alert message to some simple language. | 2022-03-08 |  | Done |  |  |  | To be Resolved
17 | Remove ss from date and time. Keep only hh and mm in format | 2022-03-08 |  | Done |  |  |  | Delivered on UAT
18 | When entity is selected as Tonga/Vanuatu nothing is shown in customer Selection dropdown | 2022-03-08 |  | In Progress | High | 6 | Amjad | To be resolved
19 | Hong long does it take to sync AX data into Portal..? Batch Job Recurrence time | 2022-03-08 |  | Pending | Low |  | Amjad | To be resolved
20 | Some Alert message needs to be revised | 2022-03-08 |  | In progress | Medium |  | Amjad | To be resolved
21 | After upload, an excel automatically download on which - left align the table content. Header center align | 2022-03-16 |  | Issue Found | Low |  | Amjad | To be resolved | This is not working in Items upload from Item selection screen
22 | Check the spacing issue on Item selection and Customer Selection screen | 2022-03-16 |  | Pending | Low |  | Amandeep | To be resolved | check feasibility
23 | Keep the User screen in Draft mode until the form is submitted for approval. | 2022-03-16 | 2022-03-25 | Done | Medium | 2 | Amandeep | Delivered on UAT | Edit and update button is provided for this functionality
24 | Remove Select an option from Item Selection Screen | 2022-03-16 | 2022-03-25 | Done | Low |  | Amandeep | Delivered on UAT
25 | Remove the Add option from Item Selection screen because it doesn’t have any purpose | 2022-03-16 | 2022-03-25 | Done | Low |  | Amandeep | Delivered on UAT
26 | To check if user can upload attachment without saving the PV form. | 2022-03-16 |  | N/A |  |  |  | To add an attachment PV number requires to be saved first, as system will ask for against which PV number the file is to be uploaded.
27 | In forms in Queue, remove the Status filter(Awaiting Approval) and keep PV number as filter only | 2022-03-16 |  | Done | Medium | 6 | Amjad | Delivered on UAT
28 | Check the Purpose of price Variance Approval and PVC dataView and its impact on different users. | 2022-03-16 |  | N/A |  |  |  | Price Variance Approval access needs to be provided to all the Approvers to whom the PV form is submitted for Approval. If not selected, approver be able to see all the submitted PV Form record but will not be able to open that PV number. Similarly PVC DataView access needs to be provided to all the user to whom Price Variance History access will be provided. If not selected, user be able to see the Price Variance History Record but cannot open any PV number.
29 | Check the Menu Options, how the hierarchy should be for menus. | 2022-03-16 |  | Done | Low |  | Amjad | Delivered on UAT
30 | After uploading the attachment, user is not able to view attachment- system throws an error. | 2022-03-16 |  | Pending | High | 5 | Amandeep | To be resolved
31 | On 1st Approval screen, if user approve and reject any line system generates duplicate records and it gets corrected only if we refresh the form | 2022-03-16 |  | Done | High | 2 |  | Delivered on UAT
32 | Change the Approve and Reject button to button view | 2022-03-16 |  | Pending | Medium | 7 | Amandeep | To be resolved | if line apporve then button green and if line reject then button is red and status coulm need to remove -change the image of red ,cross to button view
33 | After all the lines get approved, Request for change button should not be enabled | 2022-03-16 |  | Done | High | 3 | Amjad | Delivered on UAT
34 | Remove the Border from Add/Remove button | 2022-03-16 |  | Done |  |  | Amjad | Delivered on UAT
35 | On email Notification, keep the margin of the table as per the content | 2022-03-16 |  | Pending | Low |  | Amjad | To be resolved
36 | On Approved Forms, only original copy of PV form will be shown which were edited when being released to MSD. | 2022-03-16 |  | Pending | Medium | 4 | Amandeep | To be resolved
37 | Keep the Release Form editable until it is released to MSD. | 2022-03-16 | 2022-03-25 | Done | Medium | 3 | Amandeep | Delivered on UAT
38 | Make Date Non-Mandatory in PV history form | 2022-03-17 | 2022-03-25 | Issue Found | Low |  | Amandeep | To be resolved | Not all the Records are showing as per the approval level
39 | User is getting logged out when user clicks on PV form link in PV form History Page | 2022-03-17 |  | Done | High | 1 |  | Delivered on UAT
40 | Provide link on PV form on the Home Page On home Screen of user, only provide edit to Draft and change request and view access for other status. On home screen of approvers , only provide edit access to submitted PV forms which they have to approve and view access to approved PV forms. | 2022-03-17 | 2022-03-25 | Issue Found | Low |  | Amandeep | To be resolved | Copy to option should not be visible here to Approvers
41 | Make comment mandatory while Rejecting the whole PV form | 2022-03-17 |  | Done | Medium | 8 | Amjad | Delivered on UAT
42 | On PV form History, Not all PV number is showing in dropdown while filtering by PV number | 2022-03-17 |  | In progress | High | 5 | Amandeep | To be resolved | Its only showing the Rejected one's
43 | In post price setup form, correct the spelling of volume on all user level. | 2022-03-17 |  | Done | Low |  |  | Delivered on UAT
44 | On comment section, remove dash and put colon sign | 2022-03-17 |  | Done | Low |  | Amjad | Delivered on UAT
45 | Popup Close button not visible | 2022-03-17 |  | Done |  |  |  | Delivered on UAT
46 | In forms in Queue, on user screen - only provide view access to PV forms having status Submitted and Pending approval. | 2022-03-22 | 2022-03-25 | Issue Found | Medium |  | Amandeep | To be resolved | Copy to option should only be visible to users and not to Approvers
47 | Remove check box from Applicants screen in case of already existing customer group | 2022-03-24 | 2022-03-25 | Issue Found | Low |  | Amandeep | To be resolved | Remove Select an option from applicants screen where checkbox is not coming - Add/Remove button is appearing on applicants screen, of already existing group where customers record is blank
48 | In customers Selection screen, create new group is not working properly, applicants button is not working | 2022-03-24 | 2022-03-25 | Issue Found | High |  | Amandeep | To be resolved | When we create new group, upload functionality is working fine but option to select customers manually is not showing In applicants screen
49 | Remove check box from Items screen on item selection in case of already existing item group | 2022-03-24 | 2022-03-25 | Issue Found | Low |  | Amandeep | To be resolved | Remove Select an option from applicants screen where checkbox is not coming Add/Remove button is appearing on applicants screen, of already existing group where customers record is blank
50 | In Item Selection screen, create new group is not working properly, | 2022-03-24 | 2022-03-25 | Issue Found | High |  | Amandeep | To be resolved | When we create new group, upload functionality is working fine but option to select Items manually is not showing In Items screen
51 | Make Branch mandatory to add item lines, if not selected through alert message stating "Please Select the Branch" | 2022-03-24 |  | In progress | HIgh |  | Amjad | To be resolved
52 | Make Account Selection mandatory before saving the form if not selected through alert message stating "Please Select Account Selection" | 2022-03-24 | 2022-03-25 | Done | High |  | Amandeep | To be resolved
53 | Save and edit button is not working properly, its affecting the Functionality | 2022-03-24 | Amandeep | Done | High |  | Amandeep | Delivered on UAT
54 | Approve button should not be enabled on any of the approver, if any of the lines gets rejected. It should only be enabled when all the lines are approved. | 2022-03-24 |  | Pending | High |  | Amandeep | To be resolved
55 | Remove Add and Select an option from Item Selection Screen on 1st approver screen | 2022-03-24 | 2022-03-25 | Done | Medium |  | Amandeep | Delivered on UAT
56 | Unable to release data into AX | 2022-03-24 |  | Pending | High |  | Amandeep | To be resolved | Add/Remove button is appearing on applicants screen, of already existing group where customers record is blank

## New Issues
Sr.No. | Issues Raised | Issue Raised On | Status | Priority | Resource | Next line of Action | Screen
57 | Reject button on any of the Approver form should only be enabled when all the Lines are Rejected | 2022-03-25 | Pending | Medium | Amandeep | To be Resolved | All Approver screen
58 | Escalate button should only be enabled on 2nd approver screen when all the line items are approved | 2022-03-25 | Pending | Medium | Amandeep | To be Resolved | 2nd Approver Screen
59 | In PVC data view, Put space between Word and bracket in item details header. | 2022-03-25 | Pending | Low | Amandeep | To be Resolved
60 | Approver comment is not visible in PVC data view in case of rejected PV forms | 2022-03-25 | Pending | Low | Amandeep | To be Resolved
61 | Make header center aligned and content left aligned for customer Selection and Item Selection screen - also on Applicants/ Items in it. | 2022-03-25 | Pending | Low | Amandeep | To be Resolved

## Alert Message
| Steps | Level | Status | Current Alert Message | Revised Alert Message | Remarks
1 | While saving PV form | User Screen | Done | Price Variance Form saved successfully with ref: PV-XXX | PV-XXXX has been Saved
2 | While uploading attachment | User/ 1st Approver Screen | Under Testing | File uploaded successfully | File upload successful | Change the alert message on 1st approver screen as well
3 | While submitting PV form | User Screen | Done | Price Variance form submitted successfully with ref: PV-XXX | PV-XXXX has been Submitted for Approval
4 | While skipping 1st approval | User Screen | Done | Approval skipped successfully | PV-XXXX has been Redirected to Approver 2
5 | When user cancel the PV form | User Screen | Issue Found | Price variance form cancelled successfully | Are you sure you want to cancel PV-XXXX? Yes/No PV-XXXX has been Cancelled | Alert message not showing up and after clicking on Yes revised alert message is not showing up
6 | When Description is not filled | User Screen/ 1st Approver Screen/ Release User screen | Under Testing | Please Enter the Description | Please enter the Description | Spelling of Description is Incorrect in Alert message
7 | While uploading if file is not selected | User/ 1st Approver Screen | Done | Please select the file first | Please select the file first | Remove the asclamatory mark from the Alert Message
8 | While removing lines without selecting the line | All the screen except Release user | Done | Please select the line to Remove | Please select the line to remove
9 | Adding line without selecting item details | User/ 1st Approver Screen | Done | Please fill item details | Please fill in the item details
10 | When Approver proceeds to approve/Reject/Change for Request PV form without Approvers Comment | 1st/2nd/3rd Approver screen | Issue Found | Please Enter the 1st/2nd/3rd Approver Comment | Approver comment is mandatory | Keep the same Alert message when approver Reject the whole PV Form
11 | When approved by 1st approver | 1st approver | Issue Found | Price Variance form Approved successfully | PV-XXXX has been Approved | Provide space between PV number and word
12 | When approved by 2nd approver | 2nd Approver | Issue Found | Price Variance form Approved successfully | PV-XXXX has been Approved | Provide space between PV number and word
13 | When PV form rejected by any of Approver | 1st/2nd/3rd Approver screen | Issue Found | Price Variance form is reject successfully | PV-XXXX has been Rejected | Provide space between PV number and word
14 | When 2nd approver escalate the PV form | 2nd Approver | Issue Found | Price Variance form escalated successfully | PV-XXXX has been Escalated to Approver 3 | Provide space between PV number and word
15 | When approver Request for Change | 1st/2nd/3rd Approver screen | Issue Found | Request for change raised successfully (Approver-1) Price Variance form approved successfully (Approver-2) Price Variance Form is Reject Successfully (Approver-3) | You have requested for a change in PV-XXXX | Provide space between PV number and word
16 | When PV form released into AX | Release user screen |  | Price Variance synced successfully into AX. | PV-XXXX has been Released
17 | When 1st Approver and Release user clicks on update button | 1st approver/ Release user | Issue Found | Data update Successfully | PV-XXXX has been Updated | Provide space between PV number and word
18 | When approver approve/ Reject lines from header button without selecting any lines. | All Approvers | Issue Found | Please select the line | Please select the lines to Approve/Reject | Approve word in case of Approve and Reject word in case of Reject action
19 | While uploading attachment without saving the form | User Screen | Done | PV No is blank!Please Saved the data First | Please save the form to upload
20 | When user opens PV form from Draft mode and update the form | User screen | Issue Found | Data update Successfully | PV-XXXX has been Updated | Provide space between PV number and word
21 | Sync Account Selection/Sync Item Selection | Release user screen |  | Data are not available to sync to AX | Account Selection cannot be synced Item Selection cannot be synced
22 | Price Tier not selected. | User screen | Done | Please select the Price tier | Please select the Price Tier
23 | When user/1st approver delete any attachment | User/ 1st Approver Screen | Pending | Image delete successfully | File has been Removed

## Menus Hierarchy
Order:
1 | Home
2 | My Profile
3 | Price Variance Form
4 | Draft/ Changes Required Forms
5 | Post Price Set-Up Form
6 | Forms in Queue
7 | Price Variance Approval
8 | Price Variance History
9 | User Management
10 | User Hierarchy Creation
11 | Role Menu Master
12 | PVC Data View
13 | Reset Password | Check this, not working
14 | Logout