## Issues
Sr.No. | Issues Raised | Consumed Hour | Issue Raised On | Task Delivered | Status | Priority | Rank | Resource | Next line of Action | Remarks
2 | To check with the Screen Resolution | 2 | 2022-03-08 | 2022-03-31 | Done | High | 7 | Amandeep | To connect with client for session and check the Resolution setup
9 | Make all the price values having 2 decimal places. Example if entered 35.45 then it will be as it is and if entered 35 it should be 35.00 | 2 | 2022-03-08 | 2022-03-25 | Done | Medium | 5 | Amandeep | Delivered on UAT
10 | Make the Item line editable before submitting the form by user. | 5 | 2022-03-08 | 2022-03-25 | Done | Medium | 1 | Amandeep | Need to discuss as this will be a big change. | Make update button enabled only if user makes any changes in the line
22 | Check the spacing issue on Item selection and Customer Selection screen | 1 | 2022-03-16 | 2022-03-30 | Done | Low |  | Amandeep | To be resolved | check feasibility
23 | Keep the User screen in Draft mode until the form is submitted for approval. | 3 | 2022-03-16 | 2022-03-25 | Done | Medium | 2 | Amandeep | Delivered on UAT | Edit and update button is provided for this functionality
24 | Remove Select an option from Item Selection Screen | 1 | 2022-03-16 | 2022-03-25 | Done | Low |  | Amandeep | Delivered on UAT
25 | Remove the Add option from Item Selection screen because it doesn’t have any purpose | 1 | 2022-03-16 | 2022-03-25 | Done | Low |  | Amandeep | Delivered on UAT
32 | Change the Approve and Reject button to button view | 4 | 2022-03-16 | 2022-03-28 | Done | Medium | 7 | Amandeep | To be resolved | if line apporve then button green and if line reject then button is red and status coulm need to remove -change the image of red ,cross to button view
36 | On Approved Forms, only original copy of PV form will be shown which were edited when being released to MSD. | 10 | 2022-03-16 |  | Done | Medium | 4 | Amandeep | To be resolved
37 | Keep the Release Form editable until it is released to MSD. | 3 | 2022-03-16 | 2022-03-25 | Done | Medium | 3 | Amandeep | Delivered on UAT
38 | Make Date Non-Mandatory in PV history form | 2 | 2022-03-17 | 2022-03-25 | Done | Low |  | Amandeep | To be resolved | Not all the Records are showing as per the approval level
40 | Provide link on PV form on the Home Page On home Screen of user, only provide edit to Draft and change request and view access for other status. On home screen of approvers , only provide edit access to submitted PV forms which they have to approve and view access to approved PV forms. | 4 | 2022-03-17 | 2022-03-28 | Done | Low |  | Amandeep | Delivered on UAT | Copy to option should not be visible here to Approvers
42 | On PV form History, Not all PV number is showing in dropdown while filtering by PV number | 1 | 2022-03-17 | 2022-03-28 | Done | High | 5 | Amandeep | To be resolved | Its only showing the Rejected one's
46 | In forms in Queue, on user screen - only provide view access to PV forms having status Submitted and Pending approval. | 4 | 2022-03-22 | 2022-03-28 | Done | Medium |  | Amandeep | Delivered on UAT | Copy to option should only be visible to users and not to Approvers
47 | Remove check box from Applicants screen in case of already existing customer group | 2 | 2022-03-24 | 2022-03-28 | Done | Low |  | Amandeep | To be resolved | Remove Select an option from applicants screen where checkbox is not coming - Add/Remove button is appearing on applicants screen, of already existing group where customers record is blank
48 | In customers Selection screen, create new group is not working properly, applicants button is not working | 2 | 2022-03-24 | 2022-03-28 | Done | High |  | Amandeep | Delivered on UAT | When we create new group, upload functionality is working fine but option to select customers manually is not showing In applicants screen
49 | Remove check box from Items screen on item selection in case of already existing item group | 2 | 2022-03-24 | 2022-03-28 | Done | Low |  | Amandeep | Delivered on UAT | Remove Select an option from applicants screen where checkbox is not coming Add/Remove button is appearing on applicants screen, of already existing group where customers record is blank
50 | In Item Selection screen, create new group is not working properly, | 2 | 2022-03-24 | 2022-03-28 | Done | High |  | Amandeep | Delivered on UAT | When we create new group, upload functionality is working fine but option to select Items manually is not showing In Items screen
52 | Make Account Selection mandatory before saving the form if not selected through alert message stating "Please Select Account Selection" | 1 | 2022-03-24 | 2022-03-25 | Done | High |  | Amandeep | To be resolved
53 | Save and edit button is not working properly, its affecting the Functionality | 1 | 2022-03-24 | 2022-03-25 | Done | High |  | Amandeep | Delivered on UAT
54 | Approve button should not be enabled on any of the approver, if any of the lines gets rejected. It should only be enabled when all the lines are approved. | 4 | 2022-03-24 | 2022-03-28 | Done | High |  | Amandeep | Delivered on UAT
55 | Remove Add and Select an option from Item Selection Screen on 1st approver screen | 1 | 2022-03-24 | 2022-03-25 | Done | Medium |  | Amandeep | Delivered on UAT
30 | After uploading the attachment, user is not able to view attachment- system throws an error. | 1 | 2022-03-16 | 2022-03-28 | Done | High | Delivered on UAT | Amandeep | Delivered on UAT
57 | Reject button on any of the Approver form should only be enabled when all the Lines are Rejected | 1 | 2022-03-25 | 2022-03-28 | Done | Medium | Delivered on UAT | Amandeep | Delivered on UAT | All Approver screen
58 | Escalate button should only be enabled on 2nd approver screen when all the line items are approved | 1 | 2022-03-25 | 2022-03-28 | Done | Medium | To be Resolved | Amandeep | To be Resolved | 2nd Approver Screen
59 | In PVC data view, Put space between Word and bracket in item details header. | 0 | 2022-03-25 | 2022-03-25 | Done | Low | Delivered on UAT | Amandeep | Delivered on UAT
60 | Approver comment is not visible in PVC data view in case of rejected PV forms | 1 | 2022-03-25 | 2022-03-28 | Done | Low | Delivered on UAT | Amandeep | Delivered on UAT
61 | Make header center aligned and content left aligned for customer Selection and Item Selection screen - also on Applicants/ Items in it. | 2 | 2022-03-25 | 2022-03-28 | Done | Low | To be Resolved | Amandeep | To be Resolved
63 | System is submitting PV form without any item lines | 1 | 2022-03-29 | 2022-03-30 | Done | High | To be Resolved | Amandeep | To be Resolved
64 | Change the Add and Remove button on header to Plus and Minus icon | 1 | 2022-03-29 | 2022-03-29 | Done | Low | Delivered on UAT | Amandeep | To be Resolved
65 | Remove the Remove button from Item Selection screen and provide Delete bin button on header. Also change the Item "I" in upper case. | 3 | 2022-03-29 | 2022-03-30 | Done | Medium | To be Resolved | Amandeep | To be Resolved
66 | Change the header approve and Reject icon to tick and cross button view | 1 | 2022-03-29 | 2022-03-30 | Done | Medium | To be Resolved | Amandeep | To be Resolved
67 | Remove the Account selection id and itemid and show only name in selection screen | 1 | 2022-03-29 | 2022-03-30 | Done | Medium |  | Amandeep | To be Resolved
68 | show the cursor pointer on all icons | 0 | 2022-03-29 | 2022-03-30 | Done | Medium |  | Amandeep | To be Resolved
69 | change the table header left align | 0 | 2022-03-29 | 2022-03-30 | Done | Medium |  | Amandeep | To be Resolved
70 | reduce the width of the drop down in selection screen | 0 | 2022-03-29 | 2022-03-30 | Done | Medium |  | Amandeep | To be Resolved
71 | left aligh the queue form filters and font size of search bar same as other font size | 0 | 2022-03-29 | 2022-03-31 | Done | Medium |  | Amandeep | To be Resolved
72 | increase the width of the close button on selection popup | 0 | 2022-03-29 | 2022-03-31 | Done | Medium |  | Amandeep | To be Resolved
| Code Merge Activity for all points | 5
| Total | 76