## Sheet1
Sr. No. | Month | Amount
1 | May | 2430.48
2 | June | 2313.66
3 | July | 2313.66
4 | August | 2313.66
5 | September | 2313.66
6 | October | 2313.66
7 | November | 2313.66
8 | December | 2313.66
9 | January | 2313.66 | EMI | Balance
| Total | 20939.8 | 19500 | 1439.8

## Sheet2
Sr. No | Particulars | Work Type | Action By | Delivery date | Internal D date
1 | Account Selection View | New Development | Acxiom | 2022-01-22 | 2022-01-19
2 | Item Selection view | New Development | Acxiom | 2022-01-28 | 2022-01-27
3 | Sync Account selection | New Development | Acxiom | 2022-01-22 | 2022-01-21
4 | Sync Item Selection | New Development | Acxiom | 2022-01-28 | 2022-01-27
5 | Copy To - Only for finally Approved and Released | New Development | Acxiom | 2022-01-24 | 2022-01-22
6 | Option to Update End date and Description | New Development | Acxiom | 2022-01-25 | 2022-01-24
7 | Multi-selection of Account Selection Dropdown | New Development | Acxiom | 2022-01-22 | 2022-01-18
8 | Create New Temporary Customer Price Discount Group | New Development | Acxiom | 2022-01-22 | 2022-01-18
9 | Import utility for customers/Items | New Development | Acxiom | 2022-01-22 | 2022-01-22
10 | After submitting the PV form, the end date changes default to todays date | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
11 | User is able to attach the files only after saving the form and but unable to remove it at the same time, Ihave to re-open the form in draft mode to remove attachment | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
12 | Remove attachment option - can't it be something like cross button over attachment to remove if possible...or else a check box to select before each file and one single delete/Remove button instead of multiple delete button.. | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
13 | Client is facing Spacing issue on screen, too much idle space on the both side of screen | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
14 | Header Fields on row wise is not aligned properly | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
15 | Add and Remove button on user screen should be of same size and there is "+" symbol in front ofAdd so also put"-" in front of Remove. | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
16 | The font color used to search in drop down is currently white change it to black | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
17 | The font used in items Selection is different from font used in Account Selection, make it sameas account selection | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
18 | Make all the $ amount default to 2 decimal places. | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28
19 | All the Item lines details row is not properly aligned | UAT Testing Bug | Acxiom | 2022-01-31 | 2022-01-28

## Sheet3
Account selection Multiple | hour | date
multiple select in account selection | 4 | 2022-01-18
popup to make the account selection | 3 | 2022-01-18
make the grid bind to account selection | 1 | 2022-01-18
popup to make the customer application | 2 | 2022-01-20
add /remove the account selection | 2 | 2022-01-20
delete the image with check box on draft,user,approver 1 | 5
account selection on approver1,approver 2,approver 3,release user,view screen | 8 | 2022-01-19
create new price discount group user,draft,approver | 8
upload utility | 7
rename the price discount | 5
sync discount price group | 5
sync the pvc data according to the account selecrtion | 3 | 2022-01-20
add/remove the custoemr applicant | 3
56